## 01_Summary
MPSeCNet — Module Work Track Sheet
Easy tracking: Login → Dashboard → Modules ¦ When will it be complete?
Project | MPSeCNet
Flow | Login → Dashboard → Modules
Day 1 start | 18 June 2026
As-of date | 07 August 2026
Prepared by | Mayur Bobade, Associate Engineer
How to use | Use Status and Target Complete columns to track when each module will be ready
Status count
Status | Modules | Meaning
Ready | 7 | Module complete — available for use / internal check
UAT | 4 | Development complete — department testing / confirmation pending
In Progress | 2 | Development is ongoing
Not Started | 2 | Not started for current release
Pending Dept | 1 | Awaiting department decision / input
Application flow
Step 1 → Login (App / Officer / Presiding Officer)
Step 2 → Dashboard (Home)
Step 3 → Voter Services: EMS ¦ Find Voter ¦ Claim / Objection
Step 4 → About Elections: Nomination ¦ Survey ¦ Presiding Officer ¦ Expenditure
Step 5 → Next phase: EVM Scanning ¦ Reports
Step 6 → Support: Profile, Offline, Notifications

## 02_Module_Track
# | App flow | Module | Status | % Done | Started | Target complete | Latest update | What is done | Remaining (to complete)
1 | 1. Login | App Login / Officer Login | Ready | 100 | 18-Jun-2026 | Completed | 27-Jul-2026 | Guest and officer / service login working | —
2 | 1. Login | Presiding Officer Login | Ready | 100 | Jul-2026 | Completed | 05-Aug-2026 | Separate PO login with session and elector counts | —
3 | 2. Dashboard | Home Dashboard (service tiles) | Ready | 100 | 18-Jun-2026 | Completed | 07-Aug-2026 | Voter Services and About Elections home sections | —
4 | 3. Dashboard → Voter Services | EMS | UAT | 100 | 07-Aug-2026 | 08–12 Aug 2026 | 07-Aug-2026 | Home tile opens EMS login page in WebView | Department device check and sign-off
5 | 3. Dashboard → Voter Services | Find Voter | Ready | 95 | Jul-2026 | Completed | 06-Aug-2026 | Search, filters, Hindi input support, voter slip | Optional field photo edge-case check
6 | 3. Dashboard → Voter Services | Claim / Objection Application | UAT | 100 | Jul-2026 | 08–15 Aug 2026 | 27-Jul-2026 | Home tile opens claim / objection portal | End-to-end check on external portal by department
7 | 4. Dashboard → About Elections | Online Nomination (Urban) | UAT | 85 | 07-Jul-2026 | 10–20 Aug 2026 | 07-Aug-2026 | OLINAPI masters, form steps, local draft save | Department UAT and registration acceptance
8 | 4. Dashboard → About Elections | Online Nomination (Panchayat) | In Progress | 45 | 21-Jul-2026 | 25 Aug – 05 Sep 2026 | 07-Aug-2026 | Entry UI / path started | Panchayat masters and full submit flow
9 | 4. Dashboard → About Elections | Polling Station Survey | UAT | 90 | 23-Jun-2026 | 10–18 Aug 2026 | 20-Jul-2026 | Urban / rural dropdowns; survey open and save | Live survey save UAT by department
10 | 4. Dashboard → About Elections | Presiding Officer | Ready | 95 | 30-Jun-2026 | Completed | 05-Aug-2026 | Milestones, booth map, turnout, sync | Optional election-day field UAT
11 | 4. Dashboard → About Elections | Election Expenditure Accounts | Not Started | 0 | — | As per department priority | — | Portal URL identified; home release pending priority | Department go-ahead, home release, then UAT
12 | 5. Next phase (after current UAT) | EVM Scanning (CU / BU) | In Progress | 70 | 18-Jun-2026 | As per department priority | 31-Jul-2026 | Day-1 module: CU / BU and scanner screens prepared | Priority confirmation → finish and release in app
13 | 5. Next phase (after current UAT) | Reports | Not Started | 40 | Jun-2026 | As per department priority | — | Basic reports UI scaffolding | Confirm API need with department → complete
14 | 6. Support (app-wide) | Profile / Settings / English–Hindi | Ready | 95 | 23-Jun-2026 | Completed | 07-Aug-2026 | Branding, language, profile fields | Minor copy updates as requested
15 | 6. Support (app-wide) | Offline / Sync | Ready | 90 | 23-Jun-2026 | Completed | 02-Jul-2026 | Offline hub and sync queue | Optional field stress test
16 | 6. Support (app-wide) | Reminders / Notifications | Pending Dept | 75 | 28-Jul-2026 | After department timings confirmed | 29-Jul-2026 | iOS / Android notification technical fix done | Official schedule and message text from department

## 03_Dashboard_Modules
Dashboard modules — when will it be complete? (quick view)
# | Dashboard module | Status | % | Target complete | Remaining
3 | Home Dashboard (service tiles) | Ready | 100% | Completed | —
4 | EMS | UAT | 100% | 08–12 Aug 2026 | Department device check and sign-off
5 | Find Voter | Ready | 95% | Completed | Optional field photo edge-case check
6 | Claim / Objection Application | UAT | 100% | 08–15 Aug 2026 | End-to-end check on external portal by department
7 | Online Nomination (Urban) | UAT | 85% | 10–20 Aug 2026 | Department UAT and registration acceptance
8 | Online Nomination (Panchayat) | In Progress | 45% | 25 Aug – 05 Sep 2026 | Panchayat masters and full submit flow
9 | Polling Station Survey | UAT | 90% | 10–18 Aug 2026 | Live survey save UAT by department
10 | Presiding Officer | Ready | 95% | Completed | Optional election-day field UAT
11 | Election Expenditure Accounts | Not Started | 0% | As per department priority | Department go-ahead, home release, then UAT

## 04_Week_Timeline
Week | Period | Work carried out
Week 1 | 18–22 Jun 2026 | Login and Dashboard foundation; EVM scanning started (Day 1)
Week 2 | 23–29 Jun 2026 | English / Hindi; Survey WebView; Offline; Profile
Week 3 | 30 Jun–6 Jul 2026 | Presiding Officer screens started
Week 4 | 7–13 Jul 2026 | API connection; Dashboard modules expanded; Nomination started
Week 5 | 14–20 Jul 2026 | Polling Station Survey urban / rural fixes
Week 6 | 21–27 Jul 2026 | Nomination Urban; PO live turnout; branding; APK
Week 7 | 28–31 Jul 2026 | Notifications fix
Week 8 | 1–5 Aug 2026 | Presiding Officer completed
Week 9 | 6 Aug 2026 | Find Voter completed
Week 10 | 7 Aug 2026 | EMS on Dashboard; Nomination on Dashboard for UAT

## 05_Status_Meaning
Status meaning
Status | Meaning
Ready | Module complete — available for use / internal check
UAT | Development complete — department testing / confirmation pending
In Progress | Development is ongoing
Not Started | Not started for current release
Pending Dept | Awaiting department decision / input